## Sheet1
AREA | MAN HRS. | Comment
Conveyor
Mounting Conveyor CP | 20 | includes transportation, setting and mounting to floor
Conveyor CP Power Feed | 52 | includes bus plug cable tray an wiring - limited to 50ft.
21 Conv. Units field wiring | 840 | 40 man hrs per table includes mounting control hardware installing cable basket and field wiring
Mountin Local Oper. Panels | 40
Local Operator Panel Wiring | 10
Paint Robots
Mounting Robot CP's | 20 | includes transportation, setting and mounting to floor
Robot CP Power Feed | 20
2 robot units wiring | 160 | includes mounting control hardware installing cable basket and field wiring
Process
Mounting Master CP | 20 | includes transportation, setting and mounting to floor
Master CP Power Feed | 52 | includes bus plug cable tray an wiring - limited to 50ft.
Master CP Field equipment | 200
Mounting Oven Heater CP | 20 | includes transportation, setting and mounting to floor
Oven Heater CP Power Feed | 52
Oven Heater Field Equipment
Mounting ASH Heater CP | 20 | includes transportation, setting and mounting to floor
ASH Heater CP Power Feed | 52 | includes bus plug cable tray an wiring - limited to 50ft.
Lighting/Aux Equip | 120 | includes install local 120vac distribution panel, transformerpower feed and wiring for lighting
Automatic Doors | 40
Paint Kitchen | 40
TOTAL MAN HOURS | 1778
50HrWks needed with 8 man crew | 5
supervision for 5 weeks | 250Hrs
Recommended hrs budget | 2250